## Slide 1: Guide for Programming 2020
National and regional technical cooperation actions

## Slide 2
Stages of programming
Selection and prioritization of technical cooperation actions
Stage III
Preparation of document with technical cooperation and programming action
Stage IV
Identification and preliminary formulation of the demands of technical cooperation
Stage II
Update on technical cooperation offer
Stage I

## Slide 3
Stage I
Update on technical cooperation offer
Information available on the intranet
Review information shared by the programs
01
Virtual meeting with simultaneous translation.
Participate in the virtual meeting organized by DTC to clarify doubts
02
Result
Knowledge of the technical cooperation that the Hemispheric Action Programs offer

## Slide 4
Stage II:
Identification and preliminary formulation of the demands of technical cooperation
Formal request
Preparation of proposal
Presentation of country´s demands
2. Formal request for collaboration to the programs by email
4. Presentation of up to 5 demands by country (no more than 2 of the same program).
3. The teams of the Delegation, together with those of the DTC prepare a proposal for technical cooperation action as outlined in the “Technical Cooperation Action sheet”.
5. Presentation of up to 3 demands for regional technical cooperation actions.
Preliminary identification
1. Preliminary identification of topics in which is considered that technical cooperation actions can be developed
Presentation of regional demands
Result
Proposals of technical cooperation actions presented

## Slide 5
Stage III:
Selection and prioritization of technical cooperation actions
A working group will be formed to select and prioritize the demands
The Director of Technical Cooperation.
5 Managers of the Hemispheric Action Programs.
1 Coordinator of Cross-Cutting Area.
5 Representatives of delegations
2 Regional Coordinators
1 representative from the Project Management Unit
Inputs considered for defining selection criteria
This team will meet in person for a week
MTP
Alignment with tactical plan
Budgetary availability
Experiences in the countries
Technical capacity
Others

## Slide 6
Stage III:
Selection and prioritization of technical cooperation actions
1. Define criteria for selection and prioritization of technical cooperation demands.
01
2. Apply criteria to select the proposals that should be considered taking into account the existing restrictions (budgetary and operational)
02
3. Apply criteria to prioritize all demands.
03
4. Develop suggestions for improvement for prioritized demands and facilitate the channeling of those that are considered to be applied to other mechanisms.
04
05
5. Communicate to the delegations the results.
During the week´s working sessions, it is expected to:

## Slide 7
Stage IV:
Preparation of document with technical cooperation and programming action
• Managers coordinate with the proponents of the selected demands, the elaboration of a technical cooperation action document (Annex 2) “Guide for the design of cooperation projects of IICA”
1. Preparation of document of a technical cooperation action
The deadline for sending documents to DTC:
November 30, 2019

## Slide 8
Stage IV:
Preparation of document with technical cooperation and programming action
The Directorate of Technical Cooperation sends a document with technical cooperation action for the review group (DTC, Programming, Budgeting and Control Management and Planning (PBCM), Monitoring and Evaluation Management) that suggests adjustments and then sends to PBCM to enable for its implementation.
2. Presentation of document to the review group

## Slide 9
¡Thank you!

## Slide 10
Additional information

## Slide 11
Stage II:
Technical cooperation action sheet
Name or title of the Technical Cooperation action.
Applicant country or countries.
Applicant Institution / origin of demand.
Partners or allies.
Hemispheric Action Program.
Related Hemispheric Action Programs.
Articulation of activities with cross-cutting areas.
Description.
Objectives.
Main results.
Estimated cost.
Team involved in the preparation.

## Slide 12
Stage IV:
Guide for the design of cooperation projects of IICA
Name and title of a the Technical Cooperation action.
Key words.
Hemispheric action program.
Related hemispheric action programs.
Articulation of activities with cross-cutting areas.
Nature of the Technical Cooperation action*.
Objectives of the Technical Cooperation action.
Results.
Beneficiaries.
Outputs.
Output indicators and goals.
Schedule.
Global budget.
*The document specifies the expected points in this section.